Cost Management Documentation
Fitness Tracker System

# 1. Introduction

The Cost Management Plan defines how project costs will be planned, estimated, budgeted, and controlled throughout the lifecycle of the Fitness Tracker System. The objective is to ensure the project is completed within the approved budget while maintaining quality.

# 2. Cost Management Approach

The project follows PMBOK cost management processes: Cost Planning, Cost Estimation, Cost Budgeting, and Cost Control.

# 3. Cost Management Plan Components

## 3.1 Level of Accuracy

Estimates follow Budgetary Estimates with an accuracy range of ±10% to ±25%.

## 3.2 Units of Measure

Currency: USD ($). Labor: Person-Month / FTE.

## 3.3 Control Thresholds

Variance threshold is ±10%. If exceeded, corrective action is required.

## 3.4 Reporting Format

Monthly cost reports and budget vs actual comparisons.

## 3.5 Performance Measurement

Earned Value Management (EVM) will be used to monitor cost performance.

# 4. Resource Planning

## Human Resources

| Role | Quantity | Monthly Cost |
| --- | --- | --- |
| Project Manager | 1 | $8,000 |
| Backend Developers | 2 | $6,000 each |
| Frontend Developer | 1 | $5,000 |
| QA Engineer | 1 | $4,000 |
| UI/UX Designer | 1 | $4,500 |
| DevOps Engineer | 1 | $5,500 |

## Non-Human Resources

Cloud Hosting Services, Development Tools, Testing Tools, Training & Support.

# 5. Cost Estimation

## Project Management

| Activity | Cost |
| --- | --- |
| Planning & Control | $40,000 |
| Budget Management | $25,000 |
| Communication | $15,000 |
| Total | $80,000 |

## Requirements & Design

| Activity | Cost |
| --- | --- |
| Requirements Analysis | $35,000 |
| System Design | $40,000 |
| UI/UX Design | $30,000 |
| Total | $105,000 |

## System Development

| Activity | Cost |
| --- | --- |
| Backend Development | $80,000 |
| User Registration Module | $40,000 |
| Activity Tracking Module | $50,000 |
| Calories Engine | $45,000 |
| Meal Recommendation | $35,000 |
| Total | $250,000 |

## Testing & QA

| Activity | Cost |
| --- | --- |
| Test Planning | $15,000 |
| Functional Testing | $20,000 |
| UAT | $15,000 |
| Total | $50,000 |

## Deployment & Closure

| Activity | Cost |
| --- | --- |
| Deployment | $10,000 |
| Monitoring | $10,000 |
| Final Report | $5,000 |
| Total | $25,000 |

# 6. Total Cost Estimation

Base Cost = $510,000
Contingency Reserve (15%) = $76,500
Cost Baseline = $586,500
Management Reserve (10%) = $58,650
Final Project Budget = $645,150

# 7. Cost Baseline

| Phase | Cost |
| --- | --- |
| Project Management | $80,000 |
| Requirements & Design | $105,000 |
| Development | $250,000 |
| Testing | $50,000 |
| Deployment | $25,000 |
| Contingency Reserve | $76,500 |
| Total Baseline | $586,500 |

# 8. Cost Control Strategy

### Using Earned Value Management (EVM):

- Budget at Completion (BAC) = $586,500

- Planned Progress = 80%

- Actual Progress = 60%

- Actual Cost (AC) = 90% of BAC

## Step 1: Calculate Earned Value (EV)

EV = 60% × BAC = 0.60 × 586,500 = $351,900

## Step 2: Calculate Actual Cost (AC)

AC = 90% × BAC = 0.90 × 586,500 = $527,850

## Step 3: Calculate Cost Variance (CV)

CV = EV − AC = 351,900 − 527,850 = -$175,950

## Step 4: Calculate Cost Performance Index (CPI)

CPI = EV / AC = 351,900 / 527,850 = 0.67

## Interpretation

Since CV is negative, the project is over budget.

Since CPI < 1, the project is inefficient in cost performance.

## Summary Table

| Metric | Value | Status |
| --- | --- | --- |
| EV | $351,900 | Completed Work Value |
| AC | $527,850 | Actual Spending |
| CV | -$175,950 | Over Budget |
| CPI | 0.67 | Poor Cost Performance |

# 9. Conclusion

This plan ensures all costs are estimated, monitored, and controlled effectively to deliver the project within budget.