Schedule Management Documentation
Fitness Tracker System

# 1. Introduction

The Schedule Management Plan defines how the project schedule will be developed, monitored, and controlled throughout the lifecycle of the Fitness Tracker System.

# 2. Schedule Management Approach

The project follows six processes: Plan Schedule Management, Define Activities, Sequence Activities, Estimate Activity Durations, Develop Schedule, and Control Schedule.

# 3. Schedule Management Plan Components

Level of Accuracy: ±10%
Units: Days/Weeks/Months
Control Threshold: ±10%
Reporting: Weekly reports
Performance: SV and SPI

# 4. Activity Definition

| Activity ID | Activity Name |
| --- | --- |
| A1 | Project Planning & Control |
| A2 | Resource & Budget Management |
| A3 | Stakeholder Communication |
| A4 | Requirements Analysis |
| A5 | System Architecture Design |
| A6 | UI/UX Design |
| A7 | Define Visual Style Guide |
| A8 | Set Up Backend Framework |
| A9 | Design Database Schema |
| A10 | Integrate Backend Registration Endpoint |
| A11 | Develop Activity Input Interface |
| A12 | Develop Meal Input Interface |
| A13 | Implement Calorie Calculation Engine |
| A14 | Develop Goal Recommendation Module |
| A15 | Develop Meal Recommendation Module |
| A16 | Functional Testing |
| A17 | Integration Testing |
| A18 | User Acceptance Testing (UAT) |
| A19 | Set Up UAT Environment |
| A20 | Deploy Application |
| A21 | Monitoring & Alert System |
| A22 | Prepare Final Report |
| A23 | Project Closure |

# 5. Milestones

Requirements Approved, Design Completed, Development Completed, Testing Approved, System Go-Live.

# 6. Activity Sequencing

Dependencies include mandatory, discretionary, and external.
Example: Requirements → Design → Development → Testing → Deployment

# 7. Duration Estimation

Duration = Effort ÷ Resources
Development Duration = 8 weeks

# 8. Schedule Development

Tools: Gantt Chart, Network Diagram, Critical Path Method.

# 9. Schedule Baseline

| Phase | Timeline |
| --- | --- |
| Planning | Week 1–2 |
| Requirements | Week 3–4 |
| Design | Week 5–7 |
| Development | Week 8–15 |
| Testing | Week 16–18 |
| Deployment | Week 19 |

# 10. Conclusion

This plan ensures timely delivery through structured scheduling, monitoring, and control mechanisms.